## Slide 1: Project BOLT 2.0
Weekly Governance Meeting
overall_1_132270295598237589 columns_1_132270295598237589
30th Apr’ 26

## Slide 2: Go Live Status
State | City | CP Name | Current Status | Planned Rollout Date | Total Stock as per Shoper | Total Stock Scanned | Stock Approval Date | SFA Activated on | 1st ARS Order Generated | BOLT Sec Order Till Date in PCs | PCs Invoiced till date | BOLT Sec Order 16-04-26 (Total In PCs) | PCs invoiced on 16-04-26 | Fill Rate
UTTAR PRADESH | LUCKNOW | KANT DISTRIBUTORS - SPW | Billing | 06-Apr-26 | 6667 | 6582 | 10-Apr-26 | 07-Apr-26 | 15-Apr-26 | 2220 | 1722 | 306 | 236 | 78%
UTTAR PRADESH | LUCKNOW | M M DISTRIBUTORS - PR1 | Billing | 06-Apr-26 | 18474 | 17085 | 10-Apr-26 | 07-Apr-26 | 14-Apr-26 | 7345 | 5073 | 1112 | 1239 | 69%
KARNATAKA | BANGALORE | SRI BALAJI AGENCIES - BRA | Billing | 06-Apr-26 | 7931 | 7666 | 09-Apr-26 | 06-Apr-26 | 15-Apr-26 | 2355 | 1465 | 373 | 0 | 62%
KARNATAKA | BANGALORE | SRI BALAJI AGENCIES - PR1 | Billing | 06-Apr-26 | 4131 | 3666 | 09-Apr-26 | 06-Apr-26 | 15-Apr-26 | 1569 | 864 | 55 | 45 | 55%
TAMIL NADU | CHENNAI | TN-GSM AGENCIES - BRA | Billing | 08-Apr-26 | 6198 | 6136 | 10-Apr-26 | 08-Apr-26 | 15-Apr-26 | 1502 | 897 | 343 | 0 | 60%

## Slide 3
State | City | CP Name | Current Status | Planned Rollout Date | Actual Rollout | Total Stock as per Shoper | Total Stock Scanned | % Audit Completion | Stock Difference between Shoper and BOLT | Stock Approval Date | SFA Activated on | 1st ARS Order Generated | Average per day order in Pcs (LY M1) | Average per day billing in Pcs (LY M1) | Sec Order Till Date in PCs (BOLT + FA) | Average per day CY | PCs Invoiced till date (BOLT + Shoper) | Average per day CY | Count of invoices (BOLT + Shoper) | BOLT Sec Order 28-04-26 (Total In PCs) | PCs invoiced on 28-04-26 | Count of invoices on 28-04-26 | Fill Rate | Remarks
UTTAR PRADESH | LUCKNOW | KANT DISTRIBUTORS - SPW | Billing | 06-Apr-26 | 06-Apr-26 | 6,667 | 6,582 | 99% | 85 | 10-Apr-26 | 07-Apr-26 | 15-Apr-26 | 432 | 279 | 5,134 | 205 | 3,298 | 150 | 129 | 468 | 349 | 14 | 64% | Outlet cancelled the order in 1 UID and ordered in another UID. Outlet refuse to take the material mfg in 2023 and 2024. Payment issue from the market. Manpower issue.
UTTAR PRADESH | LUCKNOW | M M DISTRIBUTORS - PR1 | Billing | 06-Apr-26 | 06-Apr-26 | 18,474 | 17,085 | 92% | 1,389 | 10-Apr-26 | 07-Apr-26 | 14-Apr-26 | 891 | 434 | 17,906 | 716 | 13,561 | 616 | 296 | 2,038 | 1,325 | 29 | 76% | Wrong order taken. Repeated orders, Outlet ask to cancel the pending orders, as it's not fulfilled due to material not received from PIL. Payment issue from the market. Billing Operator is on leave today.
KARNATAKA | BANGALORE | SRI BALAJI AGENCIES - BRA | Billing | 06-Apr-26 | 06-Apr-26 | 7,931 | 7,666 | 97% | 265 | 09-Apr-26 | 06-Apr-26 | 15-Apr-26 | 189 | 326 | 4,356 | 174 | 3,638 | 158 | 120 | 285 | 264 | 8 | 84% | All secondary billing has been completed for the day
KARNATAKA | BANGALORE | SRI BALAJI AGENCIES - PR1 | Billing | 06-Apr-26 | 06-Apr-26 | 4,131 | 3,666 | 89% | 465 | 09-Apr-26 | 06-Apr-26 | 15-Apr-26 | 177 | 293 | 2,477 | 99 | 2,187 | 95 | 54 | 252 | 154 | 5 | 88% | Balance pending secondary order billing will happen tomorrow.
TAMIL NADU | CHENNAI | TN-GSM AGENCIES - BRA | Billing | 08-Apr-26 | 08-Apr-26 | 6,198 | 6,136 | 99% | 62 | 10-Apr-26 | 08-Apr-26 | 15-Apr-26 | 195 | 133 | 2,745 | 110 | 2,136 | 89 | 54 | 278 | 128 | 7 | 78% | Few secondary orders are pending for billing which CP will bill tomorrow morning.
UTTAR PRADESH | LUCKNOW | UP-M M TRADERS - SPM | Billing | 20-Apr-26 | 20-Apr-26 | 7,661 | 7,536 | 98% | 125 | 25-Apr-26 | 20-Apr-26 |  | 437 | 299 | 6,740 | 270 | 4,023 | 168 | 193 | 640 | 190 | 3 | 60% | CP will check outstanding and bill accordingly on 29th Apr 26
UTTAR PRADESH | LUCKNOW | UP-N3-KANT SERVICES - BRA | Billing | 20-Apr-26 | 20-Apr-26 | 14,558 | 14,048 | 96% | 510 | 25-Apr-26 | 20-Apr-26 |  | 676 | 412 | 12,631 | 505 | 7,827 | 326 | 262 | 548 | 97 | 5 | 62% | No issue reported so far, Sales Team will meet CP on 29th Apr 26 and confirm.

## Slide 4
State | City | CP Name | Current Status | Planned Rollout Date | Actual Rollout | 

## Slide 5: AMS Status
Sl No | Issues | Status | Remark
1 | In Inventory audit, MRP mismatch with scanned IP QR codes | Resolved | No issues reported
2 | CP unable to perform GRN - Due to config missing in prod | Resolved | No issues reported
3 | Inventory audit approval via bulk approval screen - Not working for 7k+ and also for a single style. | Resolved | No issues reported
4 | CP was unable to scan BB in the secondary invoicing screen - We found total of 1136 BBs missing which is accounting to 28%. | Resolved | No issues reported
5 | CP is unable to generate IRN in BOLT | Resolved | No issues reported
6 | CP is unable to generate IRN in BOLT | Resolved | No issues reported
7 | CP was able to view Sales Return window in 'Sold To' option in 'My Business' Menu | Resolved | No issues reported

## Slide 6: Next set of Activities
Sl No | Tasks | Status | Risk | KPMG Comments
1 | ARS Solution when triggered from Salesforce | UAT Ready | Med | Awaiting testing result by Page team for 200 bill to codes
2 | P2 to P4 tickets | Ready for UAT Deployment | Low | Currently 42 QA Passed tickets are awaiting testing by Page. Page to finalize priority of QA Passed tickets Based on Prioritization , 4-5 tickets will be tested weekly & deployed to Prod (low volume of tickets to be deployed to ensure stability)
3 | EBO | UAT Ready | Med | UAT Deployment completed by KPMG Page team to begin UAT testing from 20th Apr AMS team will work on EBO Bug reported by Page team
4 | STRIDE | Paused | High | 1. Development paused by KPMG due to 3-month delay in completion of Primary & Masters from Page team. 2. Date of completion now is 21st April from Page team. 3. KPMG team will commence integration testing with Page from 22nd April. 4. Frequent UAT deployments in BOLT 2.0 will impact HANA.

## Slide 7: EBO Activities
Sl No | Functionality | Task | Status | Due Date | KPMG Comments
1 | Secondary Orders | Syncing of Orders from Wondersoft into SFDC | UAT Ready | 9th Apr | Optimizations required were completed and shared with Page team for changes on Wondersoft end Page team had asked to create staging tables to handle volume of orders. In recent discussion, Page team has agreed to check if sending orders storewise can reduce the volume instead.
2 | Stock Allocation | As the user will not require to take any action on the Stock Allocation screen, this functionality is to be automated through batch process | UAT Ready | 13th Apr | Automation completed Dependency on HVPE to sync orders into Heroku since Stock Allocation is being conducted in Heroku for EBO. Need to arrive at a decision with Page if HVPE will sync this more frequently for EBO.
3 | Pickslip Excel Generation | As the user will not require to take any action on the Stock Allocation screen, this functionality is to be automated through batch process | UAT Ready | 15th Apr | Automation completed 1 scenario was closed with Page last week. In case of partial stock allocation, should pickslip be generated or should the order be blocked till full allocation is done.
4 | Secondary Invoicing | Invoicing secondary orders | UAT Ready | 13th Apr | We will be utilizing the GT SFA Invoicing screen for EBO invoicing as well since it has all the optimizations and the latest UI changes.
5 | Approval Processes | Std Approval Processes | UAT Ready | 13th Apr | 
6 | Retailer Onboarding | As there is no SFA, Retailer Onboarding will be done in DMS | UAT Ready | 13th Apr | This is a change request, and the details have been discussed with Page previously.
7 | EBO Reports | Changes due to Gregorian Calendar | Dev in progress | TBD | This is a change request, and the effort needs to be finalized. Currently focusing on closing Jockey CRMA issues.

## Slide 8: STRIDE Activities (Pending with Page team)
Integrations | Status | Date | Remark
Product Master | Completed |  | Integration tested
Order - PO | Completed |  | Integration tested
DB-Product Mapping | Completed |  | Integration tested
Account Master - Distributor | Completed |  | Integration tested
Geography Master | Completed |  | Integration tested
Asset Master | Ready for Testing |  | Need KPMG help to test
Invoice Create/ update | Ready for Testing |  | Need KPMG help to test
Invoice Cancellation | Ready for Testing |  | Need KPMG help to test
Inventory Color coding - Jokey/Speedo/Promo | Ready for Testing |  | Need KPMG help to test
Order Cancellation Request | Ready for Testing |  | Need KPMG help to test
BG API | Ready for Testing |  | Need KPMG help to test
SD API | Ready for Testing |  | Need KPMG help to test
BB-IP Details | Not Ready | 21-04-2026 | 
Price Master | Not Ready | 21-04-2026 | 
Payment Calculator | Not Ready | 21-04-2026 | 
DB Onboarding | Not Ready | 21-04-2026 | 
Retailer Onboarding - Create/Update | Not Ready | 21-04-2026 | 
Sales Order creation/update | Not Ready | 21-04-2026 | 
GRTF | Not Ready |  | KPMG team to confirm status. API released by Page team
Credit Management | Ready for Testing | 21-04-2026 | 
Master Credit note | On Hold |  | Part of TPM
Change request of 2 months for HANA delay – awaiting approval from Page
KPMG team will resume HANA work from 22nd April if all integrations mentioned are completed & ready for testing
Availability of same resources to be confirmed
Changes in requirements/functionality already developed will not be accommodated

## Slide 9: STRIDE Timeline
Track | Workstream | Jan |  |  |  |  |  | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  | 
 |  | 29-02 | 05-09 | 12-16 |  | 19-23 | 26-30 | 02-06 | 09-13 | 16-20 | 23-27 | 02-06 | 09-13 | 16-20 | 23-27 | 30-03 | 06-10 | 13-17 | 20-24 | 27-01 | 04-08 | 11-15 | 18-22 | 25-29 | 1-5 | 8-12 | 15-19 | 22-26 | 29-03 | 6-10 | 13-17 | 20-24 | 27-31
Setup | Org Creation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Org Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Pipeline Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DMS, SFA, CRMA | Requirement Gathering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Planned -Build Sprints |  | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual -Build Sprints |  | Sprint 1 |  |  |  |  | Sprint 2 |  |  |  | Sprint 3 |  |  |  |  |  |  |  | Sprint 4 |  | Sprint 5 |  |  |  |  |  |  |  |  |  |  | 
All | Planned – SIT |  |  | Sprint1 |  |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
All | Actual - SIT |  |  |  |  |  |  | Sprint 1 |  |  |  | Sprint 2 |  |  |  |  |  |  |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  |  |  |  |  |  |  |  | 
All | UAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | End to End Testing |  |  |  |  |  |  | 
All | Data Migration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data Setup of Masters |  |  |  |  | Data related Cutover Activities |  |  |  | 
All | Go Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Deployment & Go Live Activities |  | 
Page team has confirmed completion of development of Primary module by 21st April (Delay of ~3 months)

## Slide 10: Load Testing Status Update
Sl.No. | Module | 1 CP | 2 CPs | 100 CPs
1 | GRN-MC | Completed | Completed | Pending
2 | GRN-BB | Completed | Completed | Pending
3 | Inventory Audit | Completed | Completed | Pending
4 | SFA API for Order creation in salesforce | Completed | Completed | Pending
5 | MUB Indicator SO/DSO | Completed | Completed | Pending
6 | Style Penetration SO/DSO | Completed | Completed | Pending
7 | SFA Stock Allocation for GT | Completed | Completed | Pending
8 | SFA Pickslip Generation for GT | Completed | Completed | Pending
9 | SFA Invoicing | Completed | Completed | Pending
10 | Walk IN Order creation | In Progress | In Progress | Pending
11 | Walk IN Invoice on Status Change | In Progress | In Progress | Pending
12 | SFA App - Check in API | In Progress | In Progress | Pending
Demonstration provided for GRN MC & BB Load Testing to Page team
Test Data requirements shared with Page team

## Slide 11: Overall Timeline
Activities | 16-Mar | 23-Mar | 30-Mar | 6-Apr | 13-Apr |  | 20-Apr | 27-Apr | 4-May | 11-May | 18-May | 25-May | 01-Jun to 14-Jun | 15-Jun to 31-Jul | 01-Aug to 14-Aug | 15-Aug - 31-Aug | 1-Sep | 1-Oct | 1-Nov | 1-Dec | 1-Jan | 1-Feb | 1-Mar
Completion of E2E testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Production Deployment |  |  |  |  |  |  |  |  |  |  |  |  |  | Testing and Preparation for SAP Go live | SAP Settling time |  |  |  |  |  |  |  | 
Cutover data activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Go Live and expansion to 5 CPs |  |  |  | 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CP Support & expansion |  |  |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  | 15 |  |  | 10 | 50 |  | 100 | 300 | 400 | 400 | 70
Load Testing | Script and Data Prep |  |  |  |  |  |  |  | Test |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deploy EBO Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EBO UAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Go Live Ready for EBO |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  | 2 |  | 4 | 4 | 4 | 4 | 
Speedo Rollout |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36 |  |  |  |  | 
Modules/tasks Excluded:
Repackaging 4.Approval changes - condition based
Baseline 5. CP to CP
TPM 6. Promo secondary

## Slide 12: Sprint-wise Plan for STRIDE
Sprint 1 (05th Jan to 30th Jan) | Sprint 8 | Sprint 2 (02nd Feb to 27th Feb) | Sprint 3 (02nd Mar-21st April) | Sprint 4 ( 27th Apr-8th May) | Sprint 5 (11th May -22nd May)
Account Master (Sold To, Bill To) - Jockey | ARS Scheduling + ARS Order | SFA order placement (Jockey & Speedo) | Heroku Changes (Jockey) | DB Onboarding Integration | EBO Buyer Seller Mapping
Ship To creation for Jockey (Flow creation combining Jockey/EBO) + Logic to be added for PROMO | Purchase Order Creation(Manual) | Outlet 360 KPIs- change structure of Speedo similar to Jockey | Asset Management Jockey | Heroku Changes (Speedo) | EBO Secondary stock allocation
Jockey Product Master | Purchase Order Creation(ARS) | Homepage KPIs- change structure of Speedo similar to Jockey | SFA stock allocation and pickslip generation (Jockey & Speedo) | Trade show & Staggered order placement | EBO secondary invoicing
Speedo Product Master | Sales Order Confirmation | DB Onboarding for Speedo | SFA invoicing (Jockey & Speedo) | Bank Guarantee & Security Deposit | EBO stock transfer
Price Master (Jockey & Speedo) | Sales Order Status Update | DB Offboarding for Speedo | Stock Transfer Jockey | Account Ledger/Payment Calculator- Code removal | EBO returns
DB-Product Mapping Speedo | Primary Invoice Create | Account Master changes for Speedo | Inventory Audit Jockey | Speedo + PROMO Product Master | EBO Retailer Onboarding
Buyer-Seller Mapping | Invoice Cancellation Request | Ship To changes for Speedo | Asset Management Speedo | DB Onboarding for Speedo | Retailer Onboarding Integration (DMS+EBO)
User Master | Sales Order Cancellation Request | Retailer Onboarding | Retailer Onboarding | DB Offboarding for Speedo | GRTF & Sales Return
Route Upload | Geography Master | Limit Order | Pricing rule change (Jockey) | Secondary GRN | CRMA Reports
Buyer Seller Mapping Automation | Opportunity Outlet | Primary GRN | Pricing rule change (Speedo + PROMO) | CP-DHQ | Manager App
Dev Completed
Dev In Progress
Deferred to Next Sprint
Pending with Page

## Slide 13
Thank you